# AI-driven autonomous job scheduler for Azure Data Platform (PoC)

Objective: build an AI-powered autonomous scheduler for Azure Data Factory and Azure Databricks that optimizes resource allocation, predicts failures, minimizes cost, and continuously learns.

# 1. Architecture overview

Text summary: ADF trigger → Event Grid → AI scheduler → Decision engine → Databricks → Metrics → Feedback loop (back into AI scheduler).

Azure services used: ADF, Azure Databricks, Event Grid, Azure Monitor, Log Analytics, ADLS Gen2, Azure SQL, Azure ML, Azure Functions/Container Apps, Service Bus, Key Vault, Entra ID, Power BI.

# 2. Runtime data flow diagram

A scheduled or event-based job enters through ADF and is announced on Event Grid. The AI scheduler orchestrates prediction and optimization, the decision engine turns that into a concrete execution plan, and Databricks runs the job. Metrics from that run feed back as a reward signal that retrains the AI scheduler's models — the dashed loop on the right.

# 3. PoC phase pipeline diagram

# 4. Phase briefings

## Phase 1 — Data collection

Pulls historical run data from ADF, Databricks, Azure Monitor, and Cost Management into a Delta Lake / Azure SQL store. This is the training set every later phase depends on.

## Phase 2 — Model training

Uses Azure ML to train three predictive models — expected runtime, failure probability, and SLA-breach risk — from Phase 1's history.

## Phase 3 — Recommendation engine

Turns those predictions into concrete suggestions: cluster size, best execution window, retry count, job priority.

## Phase 4 — Optimization engine

Takes all pending jobs at once and balances queue depth, dependencies, SLAs, cluster utilization, and cost to produce a single execution plan (the Decision engine in the runtime diagram).

## Phase 5 — RL agent

Closes the loop — actual outcomes (on-time vs late, actual cost, failures) become rewards that continuously tune the scheduling policy, so the system improves without manual retraining.

# 5. Decision flow

Trigger → Predict runtime → Predict failure → Check SLA → Optimize → Execute/Delay → Collect metrics → Retrain.

# 6. Suggested schedule (12-week PoC)

A PoC of this scope needs enough historical data to train usable models before phases 2–5 can start, so Phase 1 runs partly in parallel with early Phase 2 groundwork rather than as a strict waterfall.

| Week | Phase | Key activities | Exit criteria |
| --- | --- | --- | --- |
| 1–2 | Phase 1 — Data collection | Stand up ADLS Gen2 + Azure SQL, connect ADF/Databricks/Monitor/Cost Management telemetry, backfill 30–90 days of history if available | Delta Lake tables populated; schema validated; at least one full week of live telemetry flowing |
| 3–4 | Phase 1 (cont.) + Phase 2 kickoff | Continue telemetry accumulation; feature engineering (job type, data volume, time-of-day, cluster config, historical duration/cost); baseline EDA | Feature store ready; 500+ historical job runs available |
| 5–6 | Phase 2 — Model training | Train/validate runtime, failure and SLA-breach prediction models in Azure ML; register models | Models meet baseline accuracy thresholds agreed with stakeholders |
| 7 | Phase 3 — Recommendation engine | Build service consuming model outputs to emit cluster size, window, retry, priority suggestions | Recommendations validated against held-out past jobs |
| 8–9 | Phase 4 — Optimization engine | Implement plan generator considering queue, dependencies, SLAs, utilization, cost; wire into Decision Engine | Engine produces a full plan for a simulated multi-job queue within acceptable latency |
| 10 | Integration | Connect AI Scheduler, Decision Engine, Event Grid path, Databricks execution end-to-end; add Service Bus + Key Vault | End-to-end trigger → plan → execute → metrics loop runs without manual intervention |
| 11 | Phase 5 — RL agent | Define reward function; implement policy update loop; run in shadow mode alongside static rules | Shadow recommendations logged and compared to baseline; no live control yet |
| 12 | Evaluation & reporting | Run AI-scheduled vs baseline comparison; build Power BI dashboard; document findings | Cost/SLA/utilization deltas quantified; PoC report delivered |

Notes on timing:

- Weeks are elapsed, not effort — actual person-days depend on team size (2–3 people is typical for a PoC of this scope).

- If historical telemetry already exists before the PoC starts, Weeks 1–4 can compress significantly.

- The RL agent (Phase 5) runs in shadow mode for the PoC — direct production control is a post-PoC decision.

# 7. Glossary of terms

## Azure services

| Term | What it is in this project |
| --- | --- |
| ADF (Azure Data Factory) | Orchestration service that defines and triggers the data pipeline jobs being scheduled. |
| Azure Databricks | Spark-based compute platform where the actual data jobs execute; cluster size and timing are what the AI layer optimizes. |
| Event Grid | Pub/sub eventing service that routes the ‘job ready to run’ signal from ADF to the AI Scheduler without tight coupling. |
| Azure Monitor | Collects operational telemetry (execution logs, resource metrics, alerts) used as model input. |
| Log Analytics | Query layer over Azure Monitor data; used to extract structured telemetry for the Delta Lake/SQL store. |
| ADLS Gen2 | Storage layer backing Delta Lake, holding raw and curated execution history. |
| Azure SQL | Relational store used alongside/instead of Delta Lake for structured execution metadata, useful for fast lookups. |
| Azure ML | Machine learning platform used to train, version, and serve the prediction models. |
| Azure Functions / Container Apps | Lightweight compute hosting options for the AI Scheduler and Decision Engine services. |
| Service Bus | Reliable messaging layer for passing execution plans and status between components. |
| Key Vault | Secrets and credential store referenced by all services instead of hardcoding secrets. |
| Entra ID | Identity provider handling authentication/authorization between services. |
| Power BI | Dashboarding layer for visualizing scheduling outcomes, cost savings, and SLA performance. |

## Architecture / flow terms

| Term | Meaning |
| --- | --- |
| Delta Lake | Open table format (ACID transactions on ADLS Gen2) storing execution history reliably and supporting time-travel queries for retraining. |
| AI Scheduler | The orchestrating service that receives trigger events and coordinates prediction, optimization, and execution. |
| Decision Engine | Component that turns recommendations and system state (queue, SLAs, cost) into a concrete execution plan. |
| Feedback loop | Mechanism by which actual job outcomes are captured and fed back to retrain models and RL policy. |
| Execution plan | The Decision Engine's output: which jobs run, on what cluster size, in what window, at what priority. |

## ML / RL terms

| Term | Meaning |
| --- | --- |
| Runtime prediction model | Regression model estimating how long a job will take given its features. |
| Failure prediction model | Classification model estimating probability a job run fails. |
| SLA prediction model | Model estimating probability a job will breach its deadline under current conditions. |
| SLA | The target deadline or quality bar a job must meet. |
| Recommendation engine | Suggests concrete scheduling parameters (cluster size, window, retries, priority) from model outputs. |
| Optimization engine | Reconciles recommendations across all pending jobs, resolving trade-offs (cost vs SLA vs utilization). |
| Reinforcement learning (RL) agent | A model that learns a scheduling policy by trial and reward rather than supervised labels. |
| Reward | Scalar feedback signal (e.g. weighted SLA adherence, cost, accuracy) used to judge a scheduling decision. |
| Policy | The current strategy the RL agent uses to decide scheduling actions; updated as rewards come in. |
| Shadow mode | Running a model's recommendations alongside the live system for comparison, without controlling production. |

## Decision flow terms

| Term | Meaning |
| --- | --- |
| Trigger | The initiating signal — typically a scheduled or event-based ADF pipeline start request. |
| Predict runtime / Predict failure | The two inference calls made against the trained models before a job is scheduled. |
| Check SLA | Step where the Decision Engine verifies whether the plan keeps the job within its deadline. |
| Optimize | Step where the Optimization Engine balances this job's needs against the full queue. |
| Execute/Delay | Outcome of optimization for a given job — run now, or push to a later window. |
| Collect metrics | Post-execution step capturing actual runtime, cost, and success/failure for feedback. |
| Retrain | Periodic refresh of the prediction models and RL policy using newly collected metrics. |